Provincial Round Up Program/Entertainment Task & Contact List

| Round Up Preparation |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Task # | Task Description | Completed by: | Person/Team responsible | Complete % | Notes |
|  | Resourcing/Event Space |  |  |  |  |
|  | Recruit Co Chair | Dec 01 | Program/Ent Chair | 100% | Cori elected |
|  | Prepare Program/Ent budget | Dec 01 | Program/Ent Chair | 100% | Budget completed. |
|  | Identify potential locations | Dec 01 | Chair | 100% |  |
|  | Choose location | Dec 01 | Chair/Committee | 100% |  |
|  | Reserve location | Dec 01 | Chair | 100% |  |
|  | Sign location contract and pay deposit | Jan. 01 | Chair | 100% |  |
|  | Recruit team to help with: Decorating the hall – 5 people Chairing sessions – 4 people + us | March 01 | Program/Ent Chair & Co Chair | 100% | Decoration - Noelle, Pam, Karen, Marie, Cori |
|  | Programming |  |  |  |  |
|  | Select Round Up Theme | Dec 14 | Program/Ent Chair | 100% | “Foundations of Freedom” Focuses on the foundation laid by the founders and the freedom that sobriety offers to those who follow. |
|  | Theme Approval | Dec 14 | Committee | 100% |  |
|  | Create draft program | Dec 14 | Program/Ent Chair & Co Chair | 100% |  |
|  | Review program with committee | Dec 14 | Program/Ent Chair | 100% |  |
|  | Reach out to DCMs for suggestions of speakers and panel members | Jan 17 | Program/Ent Chair & Co Chair | 100% |  |
|  | Create list of potential speaker/panel names | Jan 10 Feb.08 | Program/Ent Chair & Co Chair | 100% |  |
|  | Create list of Chairs for the sessions. | Feb. 08 | Program/Ent Chair & Co Chair | 100% | Chairs - Pam - Dani - Noelle - Melissa |
|  | Visit to groups to meet folks | Jan 10-20 Feb. 10-28 | Program/Ent Chair & Co Chair | 0% | Will do if there is an opportunity. |
|  | Select run, walk and meditation leaders | Jan 15 | Program/Ent Chair & Co Chair | 100% | Confirmed: Run - Allison (Acceptance) Walk - Erin (Acceptance) Meditation – Nathaniel |

|  | Map out the run/walk route | Jan 10 | Program/Ent Chair & Co Chair | 100% | Run Map https://maps.app.goo.gl/trVrW6t6EfLQdipz5 Walk Map https://maps.app.goo.gl/keDxbJ9hx3DrXPhW8 |
| --- | --- | --- | --- | --- | --- |
|  | Finalize Speaker/Panel Topics | Feb 15 March 31 | Program/Ent Chair & Co Chair | 100% | Reviewed with Cori and made some tweaks. We have “tracks” which are Unity, Service and Recovery. |
|  | Confirm Speakers and Panelists | Feb 20 April 15 | Program/Ent Chair & Co Chair | 100% | Spoke with several folks at the MWRU. This is in a good place. |
|  | Email follow up with Speakers and Panelists | week prior to June 06 | Program/Ent Chair & Co Chair | 100% |  |
|  | Purchase Friday and Saturday main speaker gifts | Apr 05 | Program/Ent Chair & Co Chair | 100% | blankets |
|  | Create Final Program | May 01 | Program/Ent Chair | 100% |  |
|  | Print Program | June 04 |  | 100% |  |
|  | Play |  |  |  |  |
|  | Obtain draft script for review | Nov 01 | Program/Ent Chair | 100% |  |
|  | Obtain approval for the license cost | Dec 14 | Program/Ent Chair | 100% |  |
|  | Remit payment | Jan 10 | Treasurer | 100% |  |
|  | Create and post flyer for auditions | Jan 31 | Program/Ent Chair & Co Chair | 100% |  |
|  | Select judges | Feb 07 | Program/Ent Chair & Co Chair | 100% | Marie, Cori, Judy & one more |
|  | Select audition readings | Feb 15 | Program/Ent Chair & Co Chair | 100% | Confirmed with Stepping Stones I can share excerpts for the auditions. |
|  | Book space for auditions | Feb 15 | Program/Ent Chair & Co Chair | 100% | Confirmed with Cathy at C24 |
|  | Have Auditions | Mar 15-16 | Program/Ent Chair & Co Chair | 100% | 15th is full, 16th has some spots left |
|  | Select and inform actors | Mar 31 | Program/Ent Chair & Co Chair | 100% |  |
|  | Set rehearsal times and procure space | Feb 20 | Program/Ent Chair & Co Chair | 100% |  |
|  | Visit church to familiarize with space and lighting | Apr 02 | Program/Ent Chair & Co Chair | 100% |  |
|  | Procure Props | Mar 31 | Program/Ent Chair & Co Chair | 100% |  |
|  | Procure wardrobe | Mar 31 | Program/Ent Chair & Co Chair | 100% |  |
|  | Rehearsals Start | Apr 05 March 29 | Program/Ent Chair & Co Chair | 100% | Rehearsals every week (9 rehearsals in total) |
|  | Dress Rehearsals | June 04 | Program/Ent Chair & Co Chair & Cast | 100% |  |
|  | Create Play bill |  | Program/Ent Co Chair | 100% |  |
|  | Games Night |  |  |  |  |
|  | Select games | Feb | Program/Ent Chair & Co Chair | 100% |  |
|  | Select emcees | Mar | Program/Ent Chair & Co Chair | 100% |  |
|  | Create game donation/loan sheet | Mar | Program/Ent Chair & Co Chair | 100% |  |
|  | Reach out to fellowship for game donations | Mar | Program/Ent Chair & Co Chair | 100% |  |
|  | Meet with Emcees to review format | Apr | Program/Ent Chair & Co Chair | Day of |  |
|  | Pick up games | May | Program/Ent Chair & Co Chair | 100% |  |
|  | Print score cards etc. | June | Program/Ent Chair & Co Chair | 2 days prior |  |
|  | Dance |  |  |  |  |
|  | Identify potential DJ's - Speak with Noelle to see who she uses | Dec 13 | Program/Ent Chair | 100% |  |
|  | Determine theme | Jan | Program/Ent Chair & Co Chair | 100% | Sock Hop (50’s) |
|  | Choose DJ option | Jan | Program/Ent Chair & Co Chair | 100% | Noelle suggested 2. I reached out to both. Only 1 responded. Brandon-He can do 3-4 hour show. Comes with requests and lighting. |
|  | Reserve DJ | Jan | Program/Ent Chair & Co Chair | 100% | Deposit sent to Brandon |
|  | Sign music contract and pay deposit | Jan | Program/Ent Chair & Co Chair & Treasurer | 100% |  |
|  | Buy decorations | Apr | Program/Ent Chair & Co Chair | 100% | Submitted the order and the receipt to Mary. Noelle also donated some items from the dance. |
|  | Confirm DJ | May 15 | Program/Ent Chair & Co Chair | 100% | Texted DJ, awaiting reply |
|  | Confirm with church setup requirements | May | Program/Ent Chair & Co Chair | 100% |  |
|  | Misc. |  |  |  |  |
|  | Create draft Survey for review by committee | March | Program/Ent Chair & Co Chair | 100% | 1st draft complete |
|  | Survey Approval | March | Program/Ent Chair & Co Chair | 100% |  |

| 1 week prior to the Round Up |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Task # | Task Description | Date/Time | Person/Team responsible | Complete Y/N | Notes |
|  | Print copies paper copies of survey |  |  | Y |  |
|  | Create QR code for survey – Print copies |  |  | Y |  |
|  | Procure Box for surveys |  |  | Y |  |
|  | Email all speakers and panelists to remind them |  |  | Y |  |
|  | Email/call DJ to remind |  |  | Y |  |
|  | Hold final rehearsals |  |  | Y |  |

| June 6 Friday- Day 1 of Round Up |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Task # | Task Description | Date/Time | Person/Team responsible | Complete Y/N | Notes |
|  | Arrive at church | 1pm |  | Y |  |
|  | Set up chairs and tables in big and small room including the Area Officers table(s) | 12-3 |  | Y |  |
|  | Set up Registration Chair and tables | 12-3 |  | Y |  |
|  | Set up and test technology. | 12-3 |  | Y |  |
|  | Set up Board games |  |  | Y |  |
|  | Put up signage | 12-3 |  | Y |  |
|  | Set up coffee and tea service and Ice Cream | 12-3 |  | Y |  |
|  | Committee huddle and final prep | 3:30pm |  | Y |  |
|  | Open physical doors and greet attendees | 5:30pm |  | Y |  |
|  | Registration activities | 5:00pm |  | Y |  |
|  | Welcome and Opening Remarks | 6:30pm |  | Y | Brief introduction to the roundup theme and highlights Play up the games night and ice cream social Housekeeping announcements |
|  | Speaker "Foundations of Freedom " | 6:45pm |  | Y | Speak on the theme |
|  | Ice Cream Social | 7:45pm |  | Y |  |
|  | Games Rock Paper Scissors Extreme Various games around the room | 7:45pm |  | Y | RPSE was ok but the games were a hit |
| Friday session finishes |  |  |  |  |  |
|  | Set up for next days play and speakers and panelists | Concurrently to the fellowship activities | Program/Ent Chair & Co Chair and others??? | Y |  |
|  | Help hospitality tidy up | ?? |  | Y |  |

| June 7 Saturday Day 2 of Round Up |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Task # | Task Description | Date/Time | Person/Team responsible | Complete Y/N | Notes |
|  | Program Chair and Co Chair Arrive | 7am | Program/Ent Chair & Co Chair | Y |  |
|  | Open physical doors and greet attendees | 7:45am | Program/Ent Chair & Co Chair | Y |  |
|  | Registration activities | 7:45am |  | Y |  |
|  | Direct Run/Walk folks to marshalling area | 7:45am | Program/Ent Chair & Co Chair | Y |  |
|  | Direct Meditation Participants to their area | 7:45am | Program/Ent Chair & Co Chair | Y |  |
|  | Run/Walk, Meditation & Yoga begin | 9am | Program/Ent Chair & Co Chair | Y | See notes from step 5 |
|  | Speaker and Panelists check in at registration | 9:00 | Anne | Y |  |
|  | Start the assembly as per agenda | 9:15am | All | Y |  |
| Saturday session finishes |  |  |  |  |  |
|  | Help hospitality tidy up | ?? | Host Comm, it was anyone we could grab | Y |  |

| Lessons Learned |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Task # | Task Description | Date/Time | Person/Team responsible | Complete Y/N | Notes |
|  | Review the feedback from the survey | ?? | Committee | Y |  |
|  | Review the feedback from the committee | ?? | Committee | Y |  |
|  | Make recommendations | ?? | Committee | Y |  |
| Done!!! 😊 |  |  |  |  |  |

First Aid kit location – Pastors Room

Wi-Fi - DLink-0515

Password-183p0rtlanD

Main room configuration